Biodiversity Policy Sub-Group.

10th January 2008.

Attendees

Sarah Hamley, Paul Wilkinson, Jenny Hawley, Catherine Weightman, Lesley Anderson

Apologies: Alan Wheeler, Fabiola Blum, Steve Scott, Will Akast

Action Catherine – find out if consultation with stakeholders on HLS

Action Catherine – to forward national information received.

Action Paul – to send out email re Defra Land Use meeting

Implementation Plan

Catherine to check linkages with National Strategy.

Who is the audience?

Introduction: written by Chair

Objectives for authors of implementation plan Chapters

Identify main objectives three at max

Clarify actions maximum of five [could include cross cutting]

Key Issues

Collate comments after consultation and draft the chapter

Timeline

Pre 24th Jan report to Forum on outline and ask for volunteers set up briefing mid February

Send draft to CW to collate/first edit 4th April

First draft ready for consultation 24th April send out to all on wider Forum mailing list - 10 weeks

End of consultation period 4th July – Catherine to have all comments (ideally if Forum has admin support send to them) then distribute to comments to people who wrote chapters to edit chapters by mid September

October  08 finish printed document - send out widely as possible - spend money on printing/distributing/implementation of plan - not on consultants!

Potential leads

Fragmentation

Paul Wilkinson, Steve Scott

Water

Anglian Water / Mike Drew/ John Giles [EA]

People and wildlife

Heather, Fabiola, Health person

Coastal

National Trust and Norfolk LBAP

Marine

Gen Broad Essex LBAP, Natural England – Alan and Sarah

Biodiversity Data

Martin Hicks

Monitoring

Catherine

Action Catherine to contact the suggested leads and rewrite paper ready to send out before the 24th Jan Forum meeting, and have template ready to assist the Chapter Authors.

Nerc Activities:

Possibility for further funds from Defra, each regional coordinator to take the lead with a public body – NW with Highways, East of England with Universities,

Action: Catherine to write a letter on behalf of Michael Allen to LA’s regarding the Nerc.

Information Group

First meeting 1st February 2008,

Action: Catherine to contact Go-east for an attendee and will draft an agenda with Martin Hicks and Lesley to enquire about EEDA’s Regional Intelligence Unit.

Reviewing Audit

Should we be making more reference to the document?

Action: Catherine to contact Essex to get information for revision

List of disaggregated targets are, what we’ve got and what the LBAPS need.

Catherine to have spreadsheet up dated by 24th April.

SNR

Would the Biodiversity Forum put a separate response to the consultation once it came out?

Date of next meeting 10th April – 10.15 at Ham Lane NE offices Peterborough