## Sheet1
East of England Biodiversity Forum Workplan 2007/08
| Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Cost | Priority 1-5 | Lead
Biodiversity information
Review Biodiversity Forum membership and TOR | [15 empty] | 1 | bar: March to April
UK BAP targets review - develop regional thinking on priorities and a template for LBAPs | [15 empty] | 3 | bar: March to June
Regional biodiversity data needs project | [15 empty] | 4 | bar: Feb to May
Explore link between biodiversity and geological conservation | [15 empty] | 1
Integrating biodiversity into regional policies/funding
Contribute to wards the development of a regional Climate Change Action Plan | [15 empty] | 4 | bar: March to Dec
Prepare Biodiversity Forum evidence/response to feed into the RES review | [15 empty] | 4 | bar: June to Jan
Respond to Rural Development Regulation review | [15 empty] | 3 | bar: March to June
Play a key role in the development of an Integrated Landscape/Land use Strategy | [15 empty] | 3 | bar: Feb to Sept
Take forward the production of a Regional Biodiversity Implementation Plan | [15 empty] | 5 | bar: April to March
Respond to Marine White Paper | [15 empty] | 5 | bar: April to June
Promoting biodiversity locally and regionally
Organise a biodiversity conference on a theme tba | [15 empty] | 2
Support LBAP delivery e.g. LDF guidance, opportunity mapping | [14 empty] | - | ongoing | bar: Feb to March
Identify and make links to key regional groups and panels - provide representatives to EEEF, Rural Forum, Landscape Forum, Record Centre Group, Greenspace East | [14 empty] | - | ongoing | bar: Feb to March
Take forward work on marine biodiversity e.g. workshop to explore approach | [15 empty] | 4 | bar: May to July
Take forward priority action from the communications and business plan | [15 empty] | 4 | bar: May to Aug
Remain aware of opportunities linked to the BBC Breathing Places initiative | [14 empty] | - | ongoing | bar: Feb to March
Organise workshops to promote awareness of the NERC Biodiversity Duty | [15 empty] | 4 | bar: May to Dec
Explore potential impact of Water Framework Directive on regional conservation priorities, including Cathchment Senstitive Farming | bar: June to Nov
Priorty 1= low, 5=high